## Dev Plan v2.4
Task ID | Workstream | Activity | Initiative | Task | Deliverable / Notes | Planned Start | Planned End | Duration (wd) | Depends On | Environment | Status
SINGLE-PHASE BUILD ON VZI AZURE (Mon 08-Sep to Fri 25-Sep 2026, 13 working days). Supersedes the two-phase Zensar-sandbox-then-replicate structure.
WS0 - REQUIREMENTS AND DESIGN (COMPLETE)
Task ID | Workstream | Activity | Initiative | Task | Deliverable / Notes | Planned Start | Planned End | Duration (wd) | Depends On | Environment | Status
A0.1 | WS0 | Design | I07 | Initiative 07 Functional Requirements Specification | I07 FRS v1.3 issued: criticality-tier service levels, SOP 3.1.1 conversion trigger, two-route approval gating, adoption tracking, shared I11 lead time | 4-Sep-26 | 6-Sep-26 | 3 | - | n/a | Complete
A0.2 | WS0 | Design | I08, I13 | Initiative 08 and 13 Functional Requirements Specifications | I08 FRS v1.1 and I13 FRS v1.1 issued: reservation-time assistant, PO-line grain register, evidence-based repair-PO convention, SOP aging bands, reclassification evidence | 6-Sep-26 | 6-Sep-26 | 1 | A0.1 | n/a | Complete
A0.3 | WS0 | Design | Shared | SAP OData service verification and entity dictionary update | 21 sets verified against live $metadata across both services; dictionary at v1.2 with real set and property names; gaps raised with the SAP team in failure report v3 (filter handling, paging order, $count on two sets, key completions, Z-append exposure) | 6-Sep-26 | 6-Sep-26 | 1 | - | n/a | Complete
A0.4 | WS0 | Design | Shared | Weighted progress and RAG scoring model across the SAP and AI streams | Scoring Map, Scoring Calc and Progress Report sheets; blocker override rule so a line with an unresolved blocking dependency cannot report Green | 7-Sep-26 | 7-Sep-26 | 1 | A0.3 | n/a | Complete
WS1 - VZI ENVIRONMENT AND FOUNDATIONS
Task ID | Workstream | Activity | Initiative | Task | Deliverable / Notes | Planned Start | Planned End | Duration (wd) | Depends On | Environment | Status
W1.1 | WS1 | Setup | Shared | Day-0 access verification with VZI IT: subscription, resource group, RBAC, VNet and private endpoints, Key Vault, Entra app registrations, Foundry resource and model deployments, network rules to the CPI endpoint | Checklist signed off with VZI IT (Henriette). SharePoint site and Graph consent REMOVED from the checklist: no document storage is required for these four initiatives | 8-Sep-26 | 8-Sep-26 | 1 | VZI Azure access granted 08-Sep | VZI Azure | Not Started
W1.2 | WS1 | Setup | Shared | Provision the VZI environment: resource group, ADLS Gen2, Azure SQL, App Service or Container Apps, Key Vault, Static Web App | Environment live. Provision directly and codify afterwards (W1.4); writing IaC first would put a Not Started dependency on the critical path | 8-Sep-26 | 9-Sep-26 | 2 | W1.1 | VZI Azure | Not Started
W1.3 | WS1 | Setup | Shared | Repos, branching model, CI/CD pipelines targeting VZI directly | Pipeline green on first deploy. No Zensar sandbox stage: the two-phase replication structure is withdrawn | 8-Sep-26 | 9-Sep-26 | 2 | W1.2 (partial) | VZI Azure | Not Started
W1.4 | WS1 | Development | Shared | IaC codification (Bicep or Terraform) of the provisioned environment | Re-runnable scripts with environment-specific values externalised. Now a maintainability asset rather than a replication asset, so it follows provisioning instead of preceding it | 10-Sep-26 | 11-Sep-26 | 2 | W1.2 (partial) | VZI Azure | Not Started
W1.5 | WS1 | Development | Shared | Provider-agnostic AI service layer: LLM and forecast interfaces; Foundry adapter plus one alternate; model and prompt registry externalised; retry, timeout and token logging | AI gateway module. Business logic never imports a provider SDK directly | 9-Sep-26 | 11-Sep-26 | 3 | W1.3 | VZI Azure | Not Started
W1.6 | WS1 | Integration | Shared | Entra ID SSO and role or group mapping | SSO live. The SSO stub is dropped: building straight onto Entra removes a throwaway component | 10-Sep-26 | 11-Sep-26 | 2 | W1.3, W1.1 | VZI Azure | Not Started
W1.7 | WS1 | Integration | Shared | Foundry endpoint wiring and adapter conformance tests | Foundry live behind the abstraction | 11-Sep-26 | 14-Sep-26 | 2 | W1.5 | VZI Azure | Not Started
WS2 - SAP INTEGRATION AND DATA CONTRACT
Task ID | Workstream | Activity | Initiative | Task | Deliverable / Notes | Planned Start | Planned End | Duration (wd) | Depends On | Environment | Status
W2.1 | WS2 | Integration | Shared | CPI client library: OAuth client-credentials token handling, APIPath and APIQuery construction, OData v2 envelope parsing, retry and error mapping | Reusable client. Already proven against the live endpoint from a workstation, so this is codification rather than discovery. Token handling, path construction, retry, JSON envelope parsing, ordered paging and $inlinecount are proven in cpi_discovery.py; error mapping and packaging remain. Includes extraction integrity checks: distinct-key count must equal $inlinecount after every pull, and any filter on a property not in the honoured list from filter_support.csv is applied client-side, because the service returns HTTP 200 with wrong rows on ignored filters and duplicates on unordered paging | 8-Sep-26 | 9-Sep-26 | 2 | - | VZI Azure | Complete
W2.2 | WS2 | Integration | Shared | Connectivity smoke from the VZI environment against the CPI endpoint: auth, TLS, paging | First live pull from inside VZI succeeds | 9-Sep-26 | 9-Sep-26 | 1 | W1.2, W2.1 | VZI Azure | Not Started
W2.3 | WS2 | Development | Shared | Extraction pagination with a fallback: page-until-short-page where $count is unavailable (PurchaseRequisitionSet, GoodsMovementItemSet) | Paging module. $inlinecount=allpages on the first page replaces /$count; $orderby on the entity key is mandatory on every paged call because unordered $skip returns duplicate and missing rows; page-until-short-page retained as fallback | 9-Sep-26 | 10-Sep-26 | 2 | W2.1 | VZI Azure | In Progress
W2.4 | WS2 | Development | Shared | Material-scope filter as configuration (MRP type): OAR selection expressed as a config-driven predicate on Dismm, not hard-coded | CRITICAL SEQUENCING ITEM. OAR is Dismm in (ND, PD); V1, blank and all other MRP types are excluded by VZI ruling of 08-Sep. Dismm filter is honoured server-side, so this is buildable now without any SAP change | 9-Sep-26 | 10-Sep-26 | 2 | - | VZI Azure | In Progress | Confirmation on blank
W2.5 | WS2 | Testing | Shared | Contract tests generated from live $metadata: set names, entity keys, property names and types, pagination and $count behaviour | Suite wired into CI. Generated from properties.csv and entity_sets.csv (types, lengths, annotations); records the two known /$count failures; asserts the honoured-filter list per set from filter_support.csv so a regression in filter handling is caught | 10-Sep-26 | 11-Sep-26 | 2 | W2.1 | VZI Azure | Not Started
W2.6 | WS2 | Development | Shared | Reduced mock gateway for the three sets that return no rows in this client: ReservationItemSet, MaterialValuationSet, MonthlyMovementStatisticSet | Scope reduced further: 18 of 21 sets carry data. EXTWG stub dropped after the MRP-type ruling. The two /$count failures need no mock since the data is readable via $top and $inlinecount | 9-Sep-26 | 10-Sep-26 | 2 | W2.1 | VZI Azure | Not Started
W2.7 | WS2 | Testing | Shared | Re-verify SAP services after activation, then re-run after the SAP fixes land | COMPLETE 08-Sep for the activation half: sweep run four times, ZMM_KPI02_SRV responds, Objectclas, Tabname and every reservation property captured from live $metadata. Remaining gate reuses this line: re-run the same discovery after generic $filter, default ORDER BY, $count on EBAN and MSEG and the key completions land, and compare filter_support.csv and paging_stability.txt against the 08-Sep baseline before switching from full-pull to delta ingestion | 11-Sep-26 | 11-Sep-26 | 1 | SAP team fixes F1, F3, F4, B1 (failure report v3) | VZI Azure | Complete
W2.8 | WS2 | Design | Shared | Reservation-entry BAdI launch contract with the SAP team: deep-link parameters, session-ID field designation, one BAdI routing 80-series to I08 and OAR to I13 | Contract note issued. Not in any ABAP stream today; the assistant is designed to run on demand without it | 9-Sep-26 | 10-Sep-26 | 2 | SAP team, NTT | VZI Azure | Not Started
W2.9 | WS2 | Integration | Shared | I11 lead-time source integration: consume the Z-program output | OPEN QUESTION for the SAP team: if the Z-program updates MARC-PLIFZ in place there is no work here, since MaterialPlantSet and Plifz are already live. If it writes to a Z-table, that table must be exposed on one of the two services before 15-Sep | 15-Sep-26 | 16-Sep-26 | 2 | I11 Z-program complete (SAP team, due before 15-Sep) | VZI Azure | Not Started
W2.10 | WS2 | Development | Shared | PR event listener: receive, persist and acknowledge, then wire to the live PR Event Notification interface | Off the critical path. Still blocked on the Stream 2 payload schema, which has not been shared | 16-Sep-26 | 17-Sep-26 | 2 | Stream 2 payload schema (SAP team) | VZI Azure | Not Started
WS3 - DATA PLATFORM ON LIVE DATA
Task ID | Workstream | Activity | Initiative | Task | Deliverable / Notes | Planned Start | Planned End | Duration (wd) | Depends On | Environment | Status
W3.1 | WS3 | Development | Shared | Ingestion pipelines for the 21 verified sets: CPI to ADLS raw to curated, full and delta patterns | Pipelines green on LIVE data. The synthetic-first approach is withdrawn for these sets. Delta strategy per set until the SAP fixes land: EKKO by Aedat ge then EKPO by Ebeln; MKPF by Budat eq per day then MSEG by Mblnr; EBAN, EKBE, MARC, MARD, EINA, EINE, LFA1 and MAKT as full pulls. Every pull ordered by key | 10-Sep-26 | 14-Sep-26 | 3 | W2.1, W2.3, W1.2 (partial) | VZI Azure | Not Started
W3.2 | WS3 | Development | Shared | Ingestion for the remaining seven sets on ZMM_KPI02_SRV | Completes the extraction layer. Service live; four of seven sets carry data. CDHDR by Udate ge then CDPOS by Changenr; CDPOS Fname and Value filters applied client-side | 11-Sep-26 | 15-Sep-26 | 3 | W3.1 (partial) | VZI Azure | Not Started
W3.3 | WS3 | Development | Shared | Azure SQL serving schema and curated loads: material-plant dimension, movement and PO facts, criticality; I12 duplicate crosswalk applied | Serving layer populated on live data | 14-Sep-26 | 16-Sep-26 | 3 | W3.1 | VZI Azure | Not Started
W3.4 | WS3 | Development | Shared | Criticality module: ZMM065 five-tier taxonomy as default, with AUSP or KLAH and Z-append paths behind a config switch | Single shared module consumed by I07, I08 and I13. ZZCRITIC found on MARC via change documents (failure report v3 ask G1); if confirmed and exposed it becomes the default source and ZMM065 becomes the fallback | 14-Sep-26 | 15-Sep-26 | 2 | W3.3 (partial) | VZI Azure | Not Started
W3.5 | WS3 | Development | I13 | Statistics-independent aging: derive aging bands, days since last movement, inventory turns and consumption counts from goods movements directly rather than from the LIS statistics sets | Removes two of I13's five blocked sets from the critical path and can be built before 11-Sep. Confirmed necessary: S031 is empty in this client; S032 has 1,484 rows and honours all filters | 10-Sep-26 | 11-Sep-26 | 2 | W3.1 (partial) | VZI Azure | Not Started
WS4 - I07 PREDICTIVE INVENTORY AND SAFETY STOCK (UAT 22-SEP)
Task ID | Workstream | Activity | Initiative | Task | Deliverable / Notes | Planned Start | Planned End | Duration (wd) | Depends On | Environment | Status
W4.1 | WS4 | Development | I07 | Feature engineering: consumption series, intermittency statistics (ADI and CV squared), stock positions, MRP parameters, and the supplier-weighted release-to-GRN lead time | Feature store on live data. Lead time from the I11 Z-program, expected before 15-Sep; MARC-PLIFZ as interim | 14-Sep-26 | 16-Sep-26 | 3 | W3.3 (partial); I11 Z-program (SAP team) | VZI Azure | Not Started
W4.2 | WS4 | Development | I07 | Demand classification and forecast engine: ADI and CV squared classification routing smooth materials to the I11 baseline and the rest to AI/ML; Croston and SBA baseline plus ML challenger by backtest; Safety Stock as Z times standard deviation of demand during lead time | Engine and backtest harness on live history | 15-Sep-26 | 18-Sep-26 | 4 | W4.1 (partial) | VZI Azure | Not Started
W4.3 | WS4 | Development | I07 | Criticality-tier service-level configuration: tier to target service level to Z-score | ServiceLevelConfig; percentages held as configuration pending the VZI ruling | 15-Sep-26 | 16-Sep-26 | 2 | W3.4, W4.2 (partial) | VZI Azure | Not Started
W4.4 | WS4 | Development | I07 | Recommendation API and exception queue with human-gated states and two-route approval gating: criticality tier for ROP and Max values; SOP 3.1.1 chain for conversions | FastAPI endpoints and recommendation ledger. No SAP write-back (P1) | 16-Sep-26 | 17-Sep-26 | 2 | W4.2 (partial), W1.6 | VZI Azure | Not Started
W4.5 | WS4 | Development | I07 | LLM rationale generation via the provider-agnostic layer | Rationale service and externalised prompt templates | 17-Sep-26 | 18-Sep-26 | 2 | W1.5, W4.4 | VZI Azure | Not Started
W4.6 | WS4 | Development | I07 | OAR-to-Min-Max conversion suggestion on the SOP 3.1.1 indicators: more than four consumptions in twelve months, Critical classification, or HOD-justified request; demand class as a confidence signal | Conversion candidates with indicator, supporting count and rationale. OAR scope comes from the W2.4 Dismm filter | 17-Sep-26 | 18-Sep-26 | 2 | W2.4, W4.1, W6.5 | VZI Azure | Not Started
W4.7 | WS4 | Development | I07 | Recommendation adoption tracking: change-document reconciliation on the MRP type, safety stock, reorder point and maximum stock fields; conversion adoption is a change of MRP type to VB with reorder point and maximum populated | AdoptionRecord; read-only. Pull Objectclas MATERIAL and Tabname MARC, filter Fname client-side, dedupe on the full CDPOS composite key until the MPC key fix lands. 155 planning-field changes on 69 materials are available for mechanics validation; no ND or PD to VB transition exists in the client, so conversion adoption needs a test MM02 change requested from the SAP team | 17-Sep-26 | 19-Sep-26 | 3 | W3.2, W4.4 | VZI Azure | Not Started
W4.8 | WS4 | Development | I07 | Recommendation review workbench: plant, criticality and value filters, accept, hold and reject, conversion suggestions, approval route and adoption status | First version built and running locally; deployed to VZI and extended for the FRS additions | 16-Sep-26 | 19-Sep-26 | 3 | W4.4 (partial) API contract agreed | VZI Azure | In Progress
W4.9 | WS4 | Development | I07 | Quarterly deep-dive report generation aligned to the Initiative 11 review cycle | Report template and generation job | 18-Sep-26 | 19-Sep-26 | 2 | W4.4, W4.7 (partial) | VZI Azure | Not Started
WS5 - I08 REFURBISHABLE SPARES TRACKING (UAT 17-SEP, EARLIEST OF THE THREE)
Task ID | Workstream | Activity | Initiative | Task | Deliverable / Notes | Planned Start | Planned End | Duration (wd) | Depends On | Environment | Status
W5.1 | WS5 | Development | I08 | 80-series detection rules and the repairable-universe read model | Repairable universe table and rules config. Needs none of the blocked sets, so it can start immediately. 26 80-series materials present in the client (10-digit numbers from 8000000000); normalise leading zeros before matching | 10-Sep-26 | 11-Sep-26 | 2 | W3.3 (partial) | VZI Azure | Not Started
W5.2 | WS5 | Development | I08 | Repair status register at material plus repair-PO-line grain: lifecycle read model with per-stage aging, overdue against the schedule-line delivery date plus configurable grace, and vendor turnaround analytics | Register API, read-only. Repair-PO filter proposed on evidence as item category 3 corroborated by document type ZREP, pending SAP team confirmation. Convention confirmed on live data: 3 of 4 ZREP orders carry item category 3 with account assignment F on 80-series materials. Pstyp filter is ignored server-side, so apply it on the EKPO pull | 11-Sep-26 | 15-Sep-26 | 3 | W5.1 (partial) | VZI Azure | Not Started
W5.3 | WS5 | Development | I08 | Condition-to-repair attestation: form-only capture (condition, fault category, repair-versus-scrap recommendation, optional serial, attestor, timestamp) with an evidence-reference field, plus detection of any repair PR or PO raised without a matching attestation | SCOPE CHANGE: evidence file upload is descoped, since no document storage is required. The form carries a reference field instead. Confirm and reflect in I08 FRS v1.2 | 15-Sep-26 | 16-Sep-26 | 2 | W5.2 | VZI Azure | Not Started
W5.4 | WS5 | Development | I08 | Register user interface: register view, per-stage aging alerts, exception states, attestation capture, justification log, coding candidates | First version built and running locally; deployed to VZI and extended for the FRS additions | 15-Sep-26 | 17-Sep-26 | 3 | W5.2 | VZI Azure | In Progress
W5.5 | WS5 | Development | I08 | Coding-candidate detection: LLM screening of text-only PR and PO lines and movement free text for repair-pattern language on items not 80-series coded | Scope narrowed on evidence: repair language is rare on material-coded 80-series lines but present on 165 of 5,225 text-only PO lines | 16-Sep-26 | 17-Sep-26 | 2 | W1.5, W5.2 (partial) | VZI Azure | Not Started
W5.6 | WS5 | Testing | I08 | I08 validation and UAT pack: 80-series detection against the real material master, repair-PO filter confirmation, register reconciliation | UAT READY 17-SEP. Excludes session traceability, which needs reservations and the BAdI. Client holds 4 ZREP orders and 26 80-series materials; register reconciliation is against that population | 16-Sep-26 | 17-Sep-26 | 2 | W5.2, W5.4 (partial) | VZI Azure | Not Started
WS6 - I13 SPARES UTILISATION TRACKING (UAT 22-SEP)
Task ID | Workstream | Activity | Initiative | Task | Deliverable / Notes | Planned Start | Planned End | Duration (wd) | Depends On | Environment | Status
W6.1 | WS6 | Development | I13 | Utilisation ledger, partial: deterministic stitching of PR to PO to goods receipt to issue on the live sets, without the reservation leg | Buildable before 11-Sep. The reservation leg is added at W6.2 | 10-Sep-26 | 14-Sep-26 | 3 | W3.1 (partial), W3.5 (partial) | VZI Azure | Not Started
W6.2 | WS6 | Development | I13 | Add the reservation leg to the ledger and apply the OAR material scope through the W2.4 config filter | Completes CAPTURE and STITCH. A configuration change plus one join, not a rebuild, because of W2.4 and W6.1. RESB is empty in this client; the join is built against metadata and validated only when reservation data or a fuller client is available | 11-Sep-26 | 15-Sep-26 | 2 | W6.1 (partial), W2.4 | VZI Azure | Not Started
W6.3 | WS6 | Development | I13 | WATCH metrics: months of cover, acquired versus plan, 30-day goods-received-not-issued, aging bands as configurable SOP defaults | Utilisation marts on live data | 15-Sep-26 | 16-Sep-26 | 2 | W6.2, W3.5 | VZI Azure | Not Started
W6.4 | WS6 | Development | I13 | Consumption attribution via reservation and order data; cost-centre path behind a config flag | Attribution module | 16-Sep-26 | 16-Sep-26 | 1 | W6.2 | VZI Azure | Not Started
W6.5 | WS6 | Development | I13 | Reclassification evidence per SOP 3.1.1: twelve-month consumption count, Critical flag and HOD-justified flag per OAR material | ReclassificationCandidate list; feeds W4.6 and Initiative 11; advisory only | 16-Sep-26 | 17-Sep-26 | 2 | W6.2 | VZI Azure | Not Started
W6.6 | WS6 | Development | I13 | ACT: utilisation and aging APIs, plan-breach and no-plan detection, quantity-override exceptions, requester confirmation and HOD escalation after a configurable period | API and alert engine | 17-Sep-26 | 18-Sep-26 | 2 | W6.3 | VZI Azure | Not Started
W6.7 | WS6 | Development | I13 | Utilisation dashboard: KPIs, aging buckets, non-mover drilldowns, acquired versus plan, justification log, reclassification candidates, validation views | First version built and running locally; deployed to VZI and extended for the FRS additions | 16-Sep-26 | 19-Sep-26 | 3 | W6.3 | VZI Azure | In Progress
W6.8 | WS6 | Testing | I13 | I13 validation and UAT pack: reconcile against the ZMM065 monthly report and the 30-day GR report | UAT READY 22-SEP. Excludes BAdI-triggered capture. 48% of material-plant rows have no MRP type in this client and plants outside 1300 and 1500 are present; UAT scope filtered to VZI plants | 18-Sep-26 | 22-Sep-26 | 3 | W6.6, W6.7 (partial) | VZI Azure | Not Started
WS7 - RESERVATION-TIME AI ASSISTANT (SHARED I08 AND I13)
Task ID | Workstream | Activity | Initiative | Task | Deliverable / Notes | Planned Start | Planned End | Duration (wd) | Depends On | Environment | Status
W7.1 | WS7 | Development | Shared | Reservation-context router: classify the material as 80-series, OAR or neither and route to the correct flow | Routing service. Uses the W2.4 config filter for the OAR branch | 15-Sep-26 | 16-Sep-26 | 2 | W5.1, W6.2, W2.4 | VZI Azure | Not Started
W7.2 | WS7 | Development | I08 | I08 flow: repair status, vendor and expected arrival with overdue state; repairable-unit-exists rule (80-series with stock on hand, or a removal movement with no subsequent repair PR or PO); justification capture for acquiring new | Chat flow and justification record | 16-Sep-26 | 17-Sep-26 | 2 | W5.2, W7.1 | VZI Azure | Not Started
W7.3 | WS7 | Development | I13 | I13 flow: reservation-time cross-check (stock on hand, months of cover, moving class, other-plant stock) and in-chat consumption-plan capture | Chat flow and ConsumptionPlan record | 16-Sep-26 | 18-Sep-26 | 2 | W6.2, W7.1 | VZI Azure | Not Started
W7.4 | WS7 | Development | I13 | Quantity-suggestion engine on a months-of-cover basis: trailing twelve-month consumption net of stock on hand and open POs; nudge against the configured cover ceiling; override justification | QuantitySuggestion and Justification records | 17-Sep-26 | 18-Sep-26 | 2 | W6.3, W1.5 | VZI Azure | Not Started
W7.5 | WS7 | Development | Shared | Assistant user interface, ChatSession and Justification entities, session-ID issuance, and the deep-link entry point | Usable on demand from the platform before the BAdI is live, which is what makes the 25-Sep date independent of the SAP transport | 18-Sep-26 | 22-Sep-26 | 3 | W7.2, W7.3, W7.4 | VZI Azure | Not Started
W7.6 | WS7 | Development | Shared | Session traceability and compliance: read the session identifier back from the reservation, link reservation to session to plan or justification to attestation to repair PR or PO, and raise missing-session, no-plan and unjustified-acquisition exceptions | Linkage and exception detection | 22-Sep-26 | 23-Sep-26 | 2 | W7.5, session-ID field designation (SAP team) | VZI Azure | Not Started
W7.7 | WS7 | Testing | Shared | Joint test with the SAP team: BAdI pop-up, deep link, assistant session, session identifier entered on the reservation, read-back and linkage | Dev-complete for the assistant on 25-Sep means platform-ready with the on-demand entry point live. The BAdI-triggered path follows the SAP transport and may fall after 25-Sep | 23-Sep-26 | 25-Sep-26 | 3 | W7.6, reservation-entry BAdI transported (SAP team, NTT) | VZI Azure | Not Started
WS8 - CALIBRATION, TEST AND HANDOVER
Task ID | Workstream | Activity | Initiative | Task | Deliverable / Notes | Planned Start | Planned End | Duration (wd) | Depends On | Environment | Status
W8.1 | WS8 | Testing | Shared | Data quality and volume validation: row counts, key integrity, pagination and performance tuning; daily short stand-up with the SAP team 10-18 Sep | DQ report per initiative | 14-Sep-26 | 19-Sep-26 | 5 | W3.1, W3.2 (rolling) | VZI Azure | Not Started
W8.2 | WS8 | Development | I07 | Model calibration on real history: backtests and a recommendation sanity review with the Solution Lead | OPEN DECISION: the development client holds about 2,034 materials against more than 45,000 in production, so it supports mechanics validation only. Calibration needs a fuller client or is deferred. MRP-type distribution in the client: VB 45, ND 184, PD 827 of 2,177 material-plant rows | 18-Sep-26 | 22-Sep-26 | 3 | W4.2 | VZI Azure | Not Started
W8.3 | WS8 | Development | I13 | Recalibrate moving-class bands and KPIs against the known reports | Same client-volume caveat as W8.2 | 19-Sep-26 | 22-Sep-26 | 2 | W6.3 | VZI Azure | Not Started
W8.4 | WS8 | Testing | All | System and end-to-end test across the three initiatives on VZI: live data, SSO, Foundry, assistant flows | E2E test log | 22-Sep-26 | 23-Sep-26 | 2 | WS4, WS5, WS6, WS7 (rolling) | VZI Azure | Not Started
W8.5 | WS8 | Testing | Shared | Security and POPIA review: data residency, least-privilege RBAC, access logging, confirmation of zero VZI-data egress | Review sign-off. Simplified: no document store and no Zensar sandbox to decommission | 22-Sep-26 | 23-Sep-26 | 2 | W8.4 (partial) | VZI Azure | Not Started
W8.6 | WS8 | Testing | All | Defect fix and stabilisation (24-Sep is Heritage Day, a South African public holiday; VZI-side validation is limited, offshore continues) | Punch list closed | 23-Sep-26 | 24-Sep-26 | 2 | W8.4 | VZI Azure | Not Started
W8.7 | WS8 | Release | All | UAT pack: test scripts, known-issues log, demo dataset, release notes, handover pack, and dev-complete sign-off | DEV COMPLETE 25-SEP | 24-Sep-26 | 25-Sep-26 | 2 | W8.6 | VZI Azure | Not Started
W8.8 | WS8 | Release | All | Contingency buffer | Absorbs late defects | 25-Sep-26 | 25-Sep-26 | 1 | - | VZI Azure | Not Started
WITHDRAWN FROM v2.3 - RETAINED FOR TRACEABILITY
Task ID | Workstream | Activity | Initiative | Task | Deliverable / Notes | Planned Start | Planned End | Duration (wd) | Depends On | Environment | Status
A1.1 | - | Setup | Shared | Zensar Azure sandbox provisioning | WITHDRAWN 08-Sep: never provisioned and no longer needed. VZI Azure arrived first, so the sandbox stage is redundant | - | - | - | - | - | Withdrawn
A1.2 | - | Setup | Shared | Zensar sandbox repos and CI/CD | WITHDRAWN 08-Sep: superseded by W1.3, which targets VZI directly | - | - | - | - | - | Withdrawn
A1.4 | - | Development | Shared | SSO stub with local users and roles | WITHDRAWN 08-Sep: superseded by W1.6. Building straight onto Entra removes a throwaway component | - | - | - | - | - | Withdrawn
A1.6 | - | Development | Shared | DocumentStore abstraction and Blob adapter | WITHDRAWN 08-Sep: no document storage is required for these four initiatives | - | - | - | - | - | Withdrawn
B8.5 | - | Integration | I08 | SharePoint adapter live wiring via Graph | WITHDRAWN 08-Sep: no document storage is required. SharePoint API access is no longer a delivery blocker for these initiatives | - | - | - | - | - | Withdrawn
A2.5 | - | Development | Shared | Full synthetic data fabrication framework | WITHDRAWN 08-Sep: reduced to W2.6. With 14 of 21 sets live, only the gap needs mocking | - | - | - | - | - | Withdrawn
A2.6 | - | Development | Shared | Mock gateway v2 | WITHDRAWN 06-Sep: merged into the single generic mock, now W2.6 | - | - | - | - | - | Withdrawn
EXTERNAL DEPENDENCIES AND UAT SUMMARY
Task ID | Workstream | Activity | Initiative | Task | Deliverable / Notes | Planned Start | Planned End | Duration (wd) | Depends On | Environment | Status
EXTERNAL - SAP team, requested 08-Sep, response by 09-Sep, landing asked for 11-Sep: generic $filter with all operators and rejection of unsupported predicates (F1, F3); default ORDER BY on the entity key for paged requests (F4); /$count on PurchaseRequisitionSet and GoodsMovementItemSet (B1); key completions on ChangeDocItem, PurchaseRequisition and InfoRecordOrg (C1). Blocking for delta ingestion, not for build, which proceeds on ordered full pulls. EXTERNAL - NTT, no date: pass backend error payloads through the OdataConsumption iFlow (D1).
EXTERNAL - SAP team, no date: confirm and expose ZZSTYPE, ZZCRITIC and ZZPURCLASS on MaterialPlantSet (G1); Netpr and Netwr typing; pageable, filterable and sortable annotations; Meins filter dump (F2); MBEW confirmation; Bwtar and Rsart exposure.
EXTERNAL - SAP team, due before 15-Sep: I11 supplier-weighted lead-time Z-program. Confirm whether it updates the planned delivery time in place, in which case no integration work is needed, or writes to a Z-table, which must then be exposed before 15-Sep.
EXTERNAL - SAP team and NTT, no date: reservation-entry BAdI and the session-ID field. Not in any ABAP stream. The assistant runs on demand without it, so 25-Sep does not depend on it.
UAT READINESS - I08 on 17-Sep (excludes session traceability). I07 on 22-Sep. I13 on 22-Sep (excludes BAdI-triggered capture and reservation-leg validation, RESB being empty in the client). Dev complete 25-Sep.
KEY RISK - 13 working days remain and most build tasks are Not Started. Data access is resolved; extraction runs on ordered full pulls with client-side filtering until the SAP filter and paging fixes land. The constraint is build capacity, not dependencies.

## Legend
AI Dev Plan v2.4 - Legend and change summary
Structure change | Phase A and Phase B are collapsed into a single build on VZI Azure. VZI access landed 08-Sep before any Zensar sandbox existed, so the build-then-replicate structure had no purpose.
Amber rows | New or materially respecified in v2.4.
Green rows | Complete.
Grey italic rows | Withdrawn, retained so v2.3 task IDs remain traceable.
Task ID change | Phase prefixes A and B are dropped in favour of W, since there are no longer two phases. Withdrawn rows keep their original v2.3 identifiers.
Critical sequencing | W2.4 builds the OAR material-scope filter as configuration before the external material group is exposed, so the 11-Sep fix is a config change rather than rework across I07 and I13.
Critical gate | W2.7 re-verifies the services after the 11-Sep fixes. Change-document and reservation property names are assumptions until it runs.
Resequencing | I08 moves ahead of I07. Its register needs none of the blocked sets, so it is the least blocked initiative, not the middle one.
Scope reduction | No document storage: the DocumentStore abstraction and SharePoint wiring are withdrawn, and I08 attestation becomes form-only with an evidence-reference field. Confirm in I08 FRS v1.2.
Scope reduction | Synthetic data shrinks to the eight items not yet available, since 14 of 21 sets are live and verified.
UAT readiness | I08 17-Sep, I07 22-Sep, I13 22-Sep. Dev complete 25-Sep.
Open decision | Model calibration: the development client holds about 2,034 materials against more than 45,000 in production. Either calibrate against a fuller client or defer calibration.
Open question | I11 Z-program: does it update the planned delivery time in place, or write to a Z-table that must then be exposed before 15-Sep?